## Tasks
Step No. | Task |  | Description / Prerequisites | Commands to Execute | Owner | Resource | PLANNED Start Time | PLANNED End Time | ACTUAL Start Time | ACTUAL End Time
PRE-IMPLEMENTATION
1a | Confirm prerequisites and set parameters | MOP-001 | Customer provides OCP access; Helm 3; oc; envsubst; approved CP/CFK/CMF/FKO/Flink versions; use CFK_VERSION=3.3.0 for the CFK product/operator and CFK_CHART_VERSION=0.1718.10 for the CFK Helm chart; public-registry egress to Docker Hub and packages.confluent.io; Route domain; external producer client properties; external S3/MySQL/MongoDB endpoints and credentials; and existing externally generated PKCS12/JKS keystore, truststore, and jksPassword.txt files. Use the OpenShift default SCC. Do not grant privileged or anyuid SCC. Do not hard-code UID/GID/fsGroup values. No image-pull Secret is required because this MOP uses anonymous pulls from docker.io/confluentinc. No license file or license Secret is required for this POC; record the 30-day trial expiry date. | Run: oc get scc restricted-v2 -o yaml oc get ns operator confluent flink --show-labels oc adm policy who-can use scc/restricted-v2 command -v oc helm envsubst oc whoami oc version helm version oc get clusterversion oc get nodes -o wide . ./poc-parameters.env # Display the version inputs used by this MOP. grep -E '^(export (CP_VERSION¦CFK_VERSION¦INIT_VERSION¦CFK_CHART_VERSION¦CMF_CHART_VERSION¦FKO_CHART_VERSION¦FLINK_IMAGE¦FLINK_VERSION))' poc-parameters.env # Confirm the public registry setting; do not create a registry pull Secret. test "$REGISTRY" = docker.io # Verify the Helm repository is reachable. helm repo add confluentinc https://packages.confluent.io/helm helm repo update for f in "$KRAFT_TLS_KEYSTORE_FILE" "$KRAFT_TLS_TRUSTSTORE_FILE" "$KRAFT_TLS_PASSWORD_FILE" "$KAFKA_TLS_KEYSTORE_FILE" "$KAFKA_TLS_TRUSTSTORE_FILE" "$KAFKA_TLS_PASSWORD_FILE" "$CONNECT_TLS_KEYSTORE_FILE" "$CONNECT_TLS_TRUSTSTORE_FILE" "$CONNECT_TLS_PASSWORD_FILE" "$SCHEMA_REGISTRY_TLS_KEYSTORE_FILE" "$SCHEMA_REGISTRY_TLS_TRUSTSTORE_FILE" "$SCHEMA_REGISTRY_TLS_PASSWORD_FILE" "$CONTROL_CENTER_TLS_KEYSTORE_FILE" "$CONTROL_CENTER_TLS_TRUSTSTORE_FILE" "$CONTROL_CENTER_TLS_PASSWORD_FILE"; do test -s "$f" ¦¦ { echo "Missing existing TLS file: $f"; exit 1; } done | OCP Admin | Workstation, TLS secrets | T+00:00 | T+00:15
1b | Login and create namespaces | MOP-002 | Use exactly three namespaces: operator for CFK/CMF/FKO operators, confluent for CP resources and TLS/connector Secrets, and flink for Flink custom resources and generated JobManager/TaskManager pods. | Run: oc login "$OCP_API_URL" --username="$OCP_USERNAME" --password="$OCP_PASSWORD" . ./poc-parameters.env oc apply -f 00-namespaces.yaml oc get project operator confluent flink | OCP Admin | Workstation, Kubernets operators | T+00:15 | T+00:25
1c | Create image-pull and TLS Secrets | MOP-003 | Copy the externally generated keystore/truststore/password files unchanged into separate TLS Secrets in confluent. Do not create an image-pull Secret; all Confluent images are pulled anonymously from docker.io/confluentinc. No license Secret is created. The MOP does not generate, convert, or rotate certificates. | Run: . ./poc-parameters.env # No oc create secret docker-registry command is required. # Load only the existing TLS files. chmod +x ./load-existing-tls-secrets.sh ./load-existing-tls-secrets.sh oc get secret "$KRAFT_TLS_SECRET" "$KAFKA_TLS_SECRET" "$CONNECT_TLS_SECRET" "$SCHEMA_REGISTRY_TLS_SECRET" "$CONTROL_CENTER_TLS_SECRET" -n confluent | OCP Admin / Secrets Admin | Workstation, TLS secrets | T+00:25 | T+00:40
1d | Approve external network and Route prerequisites | MOP-004 | The producer is outside OCP and publishes to the Kafka Routes. Connect and Flink run in OCP and connect outbound to S3, MySQL, and MongoDB. Confirm DNS, firewall, proxy, NetworkPolicy, TLS CA, and Kafka client settings before deployment. | Run: oc get svc router-default -n openshift-ingress oc get routes -A oc get networkpolicy -A Confirm DNS records exist for kafka.apps.customer.example.com, b0.apps.customer.example.com, b1.apps.customer.example.com, b2.apps.customer.example.com, connect.apps.customer.example.com, schemaregistry.apps.customer.example.com, and controlcenter.apps.customer.example.com. | OCP Admin / Network/DNS/security owners | Workstation, approved network change | T+00:40 | T+01:00
IMPLEMENTATION
2a | Install cert-manager, FKO, CMF, and CFK | MOP-005 | Install FKO, CMF, and CFK in operator. Public Helm charts and public Confluent images are used without pull credentials. The same OpenShift SCC model applies to CFK: use podSecurity.enabled=false so CFK does not force a fixed UID/GID. FKO and CMF use the supplied OpenShift values files. Include all three namespaces in CFK namespaceList because CFK is installed in operator and manages resources in confluent and flink. No cert-manager, image-pull Secret, or license Secret is used. CFK_VERSION is the product/operator version; CFK_CHART_VERSION is the Helm chart version passed to Helm. | Run: helm repo add confluentinc https://packages.confluent.io/helm helm repo update # CFK_VERSION is the product version; CFK_CHART_VERSION is the Helm chart version. helm show chart confluentinc/confluent-for-kubernetes --version "$CFK_CHART_VERSION" ¦ grep -E '^(version¦appVersion):' helm upgrade --install cp-flink-kubernetes-operator confluentinc/flink-kubernetes-operator -n operator --version "$FKO_CHART_VERSION" -f fko-ocp-values.yaml helm upgrade --install cmf confluentinc/confluent-manager-for-apache-flink -n operator --version "$CMF_CHART_VERSION" -f cmf-ocp-values.yaml helm upgrade --install confluent-operator confluentinc/confluent-for-kubernetes -n operator --version "$CFK_CHART_VERSION" --set image.registry=docker.io --set imagePullSecretRef="" --set enableCMFDay2Ops=true --set namespaced=true --set namespaceList="{operator,confluent,flink}" --set podSecurity.enabled=false oc get pods -n operator oc get crd ¦ grep -E "platform.confluent.io¦flink" # If a pod shows ImagePullBackOff, stop and check Docker Hub egress/proxy. Do not create a pull Secret for this MOP. oc get pods -n operator -o wide oc describe pods -n operator ¦ grep -A8 -B2 -E "ImagePullBackOff¦ErrImagePull" ¦¦ true | OCP Admin | Workstation, Kubernetes operators and custom resoruces | T+01:00 | T+01:30
2b | Deploy CP and CFK-managed external Routes | MOP-006 | Apply 01-cp.yaml in confluent. Each CP pod-producing CR contains spec.podTemplate.podSecurityContext: {} so the OpenShift default SCC assigns the namespace-valid identity. The file uses docker.io/confluentinc image paths, contains no imagePullSecrets, references existing TLS Secrets, and deploys KRaft Controllers, Brokers, Connect, Schema Registry, C3 Next Gen, and external Routes. | Run: . ./poc-parameters.env envsubst < 01-cp.yaml ¦ oc apply -f - oc get kraftcontroller,kafka,connect,schemaregistry,controlcenter -n confluent oc get routes -n confluent oc get pods -n confluent -o wide oc describe pods -n confluent ¦ grep -A8 -B2 -E "ImagePullBackOff¦ErrImagePull" ¦¦ true | OCP Admin | Workstation, Kubernetes operators and custom resoruces | T+01:30 | T+02:00
2c | Wait for CP pods and Routes | MOP-007 | Wait for all CP pods and Routes. Confirm each component is using the intended existing TLS Secret and that the external Kafka advertised hostnames match the externally generated certificate SANs. | Run: oc get pods -n confluent -w # Stop watching with Ctrl-C after all pods are Ready. oc get pvc -n confluent oc get routes -n confluent -o wide oc get secret "$KRAFT_TLS_SECRET" "$KAFKA_TLS_SECRET" "$CONNECT_TLS_SECRET" "$SCHEMA_REGISTRY_TLS_SECRET" "$CONTROL_CENTER_TLS_SECRET" -n confluent for ns in operator confluent flink; do oc get pods -n "$ns" -o custom-columns='NAME:.metadata.name,SA:.spec.serviceAccountName,UID:.spec.securityContext.runAsUser,GID:.spec.securityContext.runAsGroup,FSGroup:.spec.securityContext.fsGroup,NONROOT:.spec.securityContext.runAsNonRoot' done oc get kafka kafka -n confluent -o jsonpath="{.status.listeners.external.advertisedExternalEndpoints}"; echo oc describe kafka kafka -n confluent ¦ tail -80 | OCP Admin | Workstation, Kubernetes operators and custom resoruces | T+02:00 | T+02:30
2d | Deploy Flink JobManager and TaskManager workload | MOP-008 | Apply 02-flink.yaml in flink. FKO creates the JobManager and TaskManager pods; do not create Deployments manually. FlinkApplication contains an empty podSecurityContext under both JobManager and TaskManager pod templates so OpenShift assigns the identity. | Run: . ./poc-parameters.env envsubst < 02-flink.yaml ¦ oc apply -f - oc get cmfrestclass,flinkenvironment,flinkapplication -n flink -o wide oc get pods -n flink -w # Stop watching with Ctrl-C after the Flink JobManager and TaskManager are Ready. | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | Workstation, Kubernetes operators and custom resoruces, Flink jobs | T+02:30 | T+03:00
2e | Deploy S3, MySQL, and MongoDB sink connectors | MOP-009 | Deploy the S3, MySQL, and MongoDB sink Connector CRs. Use existing target-side TLS files only if the customer endpoint requires TLS/mTLS; this MOP does not generate target certificates. | Run: . ./poc-parameters.env oc get connect connect -n confluent -o jsonpath="{.status.phase}"; echo envsubst < 03-connectors.yaml ¦ oc apply -f - oc get connector -n confluent -w # Stop watching with Ctrl-C after all three connectors are RUNNING. | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | Workstation, Kubernetes operators and custom resoruces, available target systems (S3, MariaDB, MongoDB) | T+03:00 | T+03:20
TESTING
3a | Validate Routes and external Kafka producer | MOP-010 | Run from the external producer host. Keep the producer keystore/truststore files on that host; do not copy them into OCP. The producer client properties must reference those existing files and trust the Kafka Route certificate chain. | Run on the OCP workstation: oc get routes -n confluent -o wide oc get kafka kafka -n confluent -o jsonpath="{.status.listeners.external.advertisedExternalEndpoints}"; echo Run on the external producer host: test -s "$SOURCE_KEYSTORE_FILE" test -s "$SOURCE_TRUSTSTORE_FILE" kafka-topics --bootstrap-server "$KAFKA_EXTERNAL_BOOTSTRAP" --command-config "$SOURCE_CLIENT_PROPERTIES" --list kafka-topics --bootstrap-server "$KAFKA_EXTERNAL_BOOTSTRAP" --command-config "$SOURCE_CLIENT_PROPERTIES" --describe --topic "$SOURCE_TOPIC" printf "route-test\n" ¦ kafka-console-producer --bootstrap-server "$KAFKA_EXTERNAL_BOOTSTRAP" --producer.config "$SOURCE_CLIENT_PROPERTIES" --topic "$SOURCE_TOPIC" | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | External producer host | T+03:20 | T+03:40
3b | Validate sink connector tasks and external targets | MOP-011 | Validate Connector task status and each external target. If S3, MySQL, or MongoDB requires a customer-specific CA or mTLS setting, reference the already generated target truststore/keystore in the connector configuration approved for that target. | Run: oc get connector -n confluent oc describe connector s3-sink -n confluent oc describe connector mysql-sink -n confluent oc describe connector mongodb-sink -n confluent CONNECT_POD=$(oc get pods -n confluent -l app=connect -o jsonpath="{.items[0].metadata.name}") oc logs "$CONNECT_POD" -n confluent --tail=200 Verify S3 objects, MySQL rows in table source_topic, and MongoDB documents in database poc and collection source_topic. | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | Workstation, Kubernetes operators and custom resoruces, available target systems (S3, MariaDB, MongoDB) | T+03:40 | T+04:00
3c | Validate Flink JobManager and TaskManager | MOP-012 | Confirm the Flink application is stable and the generated JM/TM pods are Ready. Verify that the admitted pod identity is assigned by OpenShift and no pod is running privileged or with a fixed customer-supplied UID. | Run: oc get flinkapplication flink-app -n flink -o yaml oc get flinkdeployment -n flink oc get pods -n flink -l platform.confluent.io/origin=flink oc get pods -n flink -o custom-columns='NAME:.metadata.name,UID:.spec.securityContext.runAsUser,GID:.spec.securityContext.runAsGroup,FSGroup:.spec.securityContext.fsGroup,NONROOT:.spec.securityContext.runAsNonRoot' oc logs -n flink -l component=jobmanager --tail=100 oc logs -n flink -l component=taskmanager --tail=100 | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | Workstation, Kubernetes operators and custom resoruces, Flink jobs | T+04:00 | T+04:15
3d | Capture implementation evidence and acceptance | MOP-013 | Save command output and record external Route hostnames, Kafka advertised endpoints, connector task states, sink validation, Flink status, and the admitted security contexts. Record that no privileged/anyuid SCC was granted and retain the 30-day trial expiry date. | Run: oc get pods -A -o wide > evidence-pods.txt oc get routes -A -o wide > evidence-routes.txt oc get events -A --sort-by=.lastTimestamp > evidence-events.txt oc get scc restricted-v2 -o yaml > evidence-scc-restricted-v2.yaml oc get pods -A -o custom-columns='NAMESPACE:.metadata.namespace,NAME:.metadata.name,SA:.spec.serviceAccountName,UID:.spec.securityContext.runAsUser,GID:.spec.securityContext.runAsGroup,FSGroup:.spec.securityContext.fsGroup,NONROOT:.spec.securityContext.runAsNonRoot' > evidence-pod-security-contexts.txt oc get connector -n confluent -o yaml > evidence-connectors.yaml oc get flinkapplication flink-app -n flink -o yaml > evidence-flink.yaml | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | Workstation | T+04:15 | T+04:30
POST-IMPLEMENTATION
4a | Hand over the POC | MOP-014 | Provide the applied YAML files, Route/DNS list, external Kafka client settings, connector names, target validation results, versions, known limitations, and the recorded 30-day POC trial expiry date. Record that public Confluent images were used without image-pull Secrets. Do not distribute passwords or private keys. | Run: helm list -A oc get all -n confluent oc get all -n operator oc get all -n flink oc get secret -n operator oc get secret -n confluent oc get secret -n flink | OCP Admin / Data Engineer / Application Engineer / Integration Engineer | Workstation | T+04:30 | T+04:45
BACKOUT
5a | Stop and remove connectors | MOP-015 | Stop external producers first. Delete the three Connector CRs and connector credential Secrets. Retain sink data unless the data owner approves deletion. Keep the externally generated keystore/truststore files on the workstation. | Run: oc delete -f 03-connectors.yaml -n confluent oc get connector -n confluent oc delete secret s3-credentials mysql-credentials mongodb-credentials -n confluent --ignore-not-found | OCP Admin | Workstation | T+00:00 | T+00:10
5b | Delete Flink and CP resources | MOP-016 | Delete FlinkApplication first, then CP resources. Do not delete or regenerate the externally generated TLS files. | Run: oc delete -f 02-flink.yaml oc delete -f 01-cp.yaml oc get pods -n confluent oc get pods -n flink oc get pvc -n confluent oc get pvc -n flink | OCP Admin | Workstation | T+00:10 | T+00:30
5c | Remove Routes, operators, and namespaces | MOP-017 | Delete the POC TLS Secrets, uninstall operators, and delete the three POC namespaces. No image-pull Secret was created, so there is no registry Secret to delete. Do not remove or alter the cluster SCC. Do not delete customer source keystores/truststores from the workstation or shared cluster resources. | Run: oc delete secret "$KRAFT_TLS_SECRET" "$KAFKA_TLS_SECRET" "$CONNECT_TLS_SECRET" "$SCHEMA_REGISTRY_TLS_SECRET" "$CONTROL_CENTER_TLS_SECRET" -n confluent --ignore-not-found helm uninstall confluent-operator -n operator helm uninstall cmf -n operator helm uninstall cp-flink-kubernetes-operator -n operator oc delete project confluent operator flink oc get projects ¦ grep -E "confluent¦operator¦flink" ¦¦ true | OCP Admin | Workstation | T+00:30 | T+00:45